## BU_Concordat_AP_2022
HREiR Action plan 2022-25
Details
| Institution name: | Bangor University |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 5 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 29th July 2022 |  |  |  | Research-only staff |  | 227
| Institutional context: | The University’s new Strategy 2030 was approved in July 2021. It is an ambitious values-led strategy outlining our direction of travel for the next decade. The foundation of the Strategy is four pillars of Research Excellence, transformative learning experiences, an excellent student experience, and a thriving Welsh language and bilingual environment. Alongside this stands the new Research and Impact strategy which lays the foundations for growth and demonstrates the significant weight that Bangor University (BU) places on its research and impact activities. Three College-level research institutes, each under a Director, have been established to facilitate the delivery of the research and impact strategy. These research institutes will provide College-specific strategic direction, drive delivery against strategic research targets and encourage interdisciplinary research. The audience of the Concordat at BU is defined as research-only staff, staff on Teaching & Research contracts and post-graduate research students. The action plan therefore covers the development and support of researchers at all career stages and was developed jointly by individuals/groups/departments supporting research and researchers at BU. Researcher development for research staff sits within Staff Development in HR. Doctoral School provides support and training for PGRs and supervisors.The Integrated Impact and Research Support Service (IRIS) supports all academics and researchers with funding applications, financial management of the grant portfolio, guidance on REF and Impact, Open Access, research data management, technology transfer, working with businesses, assistance with IP and contracts, major projects and collaborative opportunities. [NB: BU did not take part in CEDARS 2021; many success measures in the AP 2020-22 Action Plan were defined around results of CEDARS; we have provided data from alternative consultations where possible] |  |  |  | Postgraduate researchers |  | 730
[6 empty] | T&R (Teaching & Research) staff |  | 280
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. The Strategic Concordat Group has identified building an inclusive, supportive and fair research culture and embedding equality, diversity and inclusion into our research-related policies and practices as a priority in this action plan in line with sector-wide challenges and changes to research culture . Our Staff Survey 2022 showed that Employee engagement (a measure across a number of engagement-related questions) was 68% for research staff and 60% for academic staff. Our Concordat Survey 2022 showed that 78% of respondents were aware of the Concordat (45% indicating they had heard of it and 33% indicating they had some understanding of it). An Annual Concordat progress report is presented to Council and regular Concordat updates are included in the Staff Bulletin (sent to staff and PGR mailing list). Researcher Inductions that signpost to the Concordat and the obligations under the Concordat are held twice a year. PGRs are made aware of the Concordat at PGR Inductions which are held in Years 1, 2 and 3. PGR consultation happens at meetings between the Doctoral School and PGR College and School Directors, the PGR committees (Doctoral School Board and Postgraduate Degrees Committee) and through regular meetings with the SU, QA, and with the PVC Research. PGR is represented at BU Senate by the PGR Dean. PGRs. The PRES survey data highlights any PGR issues. PRES feedback feeds into an annual Action Plan – these are formulated following school level meetings, a BU wide event, and smaller focus groups. A review of actions takes place in September following generation of the survey reports in July. Each School then generates a PRES action plan. The Doctoral School supports focus groups and necessary local initiatives to address identified PGR needs. A range of doctoral training workshops are available to all PGRs, and to Doctoral Supervisors, including specific EDI training. The Doctoral School meets regularly with the PGR College and School Directors, PGR representatives, the SU, and all other relevant stakeholders. PGR inductions are offered 3 times a year, and are now offered by Colleges to PGRs in year one, two and three of their PhD. A review of the Concordat and its importance for PGRs is presented at these events.
ECI1 | Ensure all relevant staff are aware of the Concordat. | ECI1a All new research-only staff receive Welcome email with a link to the Concordat, the Researcher Development Programme and a list of key contacts etc. Develop welcome email for new T&R staff (see EI2b) ECI1b There are currently gaps in our data regarding how "research managers" are identified - data held in HR is by role profile/grade but data on grant capture and associated externally funded research posts is held in IRIS. With a new HR/Payroll System (iTrent) being implemented by April 2023, we will be working to link up our data in order to be able to identify and support PIs/Research Managers, in particular those new to line-managing research staff. (see EI4a) ECI1c Guide to the Management and Employment of Contract Research Staff to be updated to highlight expectations around Research Integrity (see ECI5/ECM2/ESM3 ), EDI (see ECI4/ECM1) and Health & Well-being. When systems in place to identify managers of researchers (ECI1e), an information pack including this Guide and the Concordat document, as well as details of training and support available to be sent to all managers/PIs. ECI1d HR/IRIS to deliver joint sessions to introduce the Concordat and give an overview of BU Researcher Development Programme and how it maps onto Vitae's RDF session (see also PCDI1, PCDI3b) Doctoral School ECI1e Create a section regarding the Concordat on the Doctoral School webpages to raise awareness of Concordat amongst PGRs ECI1f The Concordat document will be sent to all new Doctoral Supervisors and it will be included in Doctoral Supervisor training as a resource. References to the Concordat are presented in PGR inductions in years 1, 2 and 3. | no no no no yes no | from 09/22 04/23 01/23 First session 09/22; repeat in Semester 2 11/22 11/22 | ASRCM (HR) HR/IRIS ASRCM (HR)/ Training Officer (HR) HR/IRIS DS Manager DS Manager | ECI1a+d: CEDARS 2023: minimum 80% of respondents are aware of Concordat (50% have some understanding; another 30% have heard of it). At least 65% are aware of the support BU provides for their career and professional development. ECI1b+c: System in place to identify PIs/Managers of researchers and make them aware of Concordat and their obligations. ECI1e+f: CEDARS 2023 will give us a baseline measure of awareness of Concordat amongst PGRs. | The Concordat at Bangor also covers PGRs; our actions therefore aim to ensure awareness of Concordat amongst research staff and PGRs. As noted above, BU did not take part in CEDARS 2021 but will take part in CEDARS 2023 and this will allow us to survey research staff and PGRs.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | IRIS ECI2a Consultancy Policy and Intellectual Property Policies are currently both under a large consultative review with revised policies due in 2023. Equality Impact Assessments of the policies will be undertaken to ensure policies are fair and equitable. Open Access policy will be reviewed and updated as necessary, undertaking an Equality Impact Assessment. Due Diligence Policy also under review in partnership with the Governance team and an Equality Impact Assessment of the policy also to be undertaken (see also ECR2). ECI2b IRIS to develop a course for academic managers and Heads of School to ensure that they are fully aware of policies and processes affecting their research staff. HR - Dignity at Work and Study policy and Equality, Diversity & Inclusion Policy (see actions in ECI3). - Fixed-term contract policy has recently been reviewed by the Anti-Casualisation Group (a joint HR/UCU Group) (see EI6) - Updated Guidance on our Recruitment & Selection policy has been published (see actions EI1) - Flexible Working Policy and Dynamic Working Principles (see actions ECM4) Governance ECI2c A new Research Integrity policy has recently been developed (see ECI5b). Doctoral School ECI2d Code of Practice for PGRs who teach (currently under review): PGR Maternity, Paternity and Adoption Policy are currently being developed/reviewed and will be rolled out in the new academic year. | no no no no | 06/23 06/23 06/23 by end of 22/23 | Director IRIS Director IRIS Research Integrity Officer (Governance) DS Manger | ECI2a+b: Reviews of policies are completed and Equality Impact Assessments of policies ensure our practices are inclusive, equitable and transparent. Training course delivered and policies and process communicated by HoS/Managers to all research staff. Evaluation of training course shows that HoS/Managers find the training useful (70% agree or strongly agree). Increased awareness of the policies and impact on research staff. ECI1c: see success measure ECI5b ECID2: Code of Practice for PGRs who teach, and PGR Maternity, Paternity and Adoption Policy published and communicated to PGRs. | IRIS Submission time frames for research proposal submission may currently be putting unfair demands on researchers working part-time which may disproportionally affect women as a greater proportion of women compared to men work part-time (32%F, 16% M of "Concordat" staff work part-time) This will feed into the revised Guidelines for staff preparing applications for Research Grants. The UKRI block grant at Bangor allocates funds on a first come first serve basis to ensure it gets spent. This again maybe inadvertently working better for those who work full-time and follow more traditional working patterns. Doctoral School PGR regulations are continuously reviewed, as appropriate. Reviews of policies and practices relevant to (postgraduate) research are reviewed four times a year at Doctoral committees (Doctoral School Boards; Postgraduate Research Degree Committees).
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Research Staff ECI6a BU to take part in CEDARS from 2023. Response rate to CROS 2019 was 18%, response rate to 2022 Concordat Survey was 20% ECI6b Bi-annual focus groups (with ECRs/post-docs, new T&R lecturers, PIs) will inform our Concordat Progress and AP implementation and development and will focus on topics such as "What are my obligations under the Concordat", "Barriers to Concordat Implementation" etc. RDCG to plan schedule of focus groups for this award period in Sep 2022 meeting. We will look into ways of ensuring input from a range of voices/opinions are heard for example by inviting a randomly selected group of a certain cohort (eg ECRs, PIs) ECI6c BU is committed to running bi-annual Staff surveys; the next survey will be in 2024. While the survey does not specifically look at research environment and culture, it allows us to compare the response between academic and research staff, and between those on permanent and fixed-term contracts .The response rate to the 2022 Staff survey was 58%. ECI6d PVC Research & Innovation led four Research Roadshows during 21/22, one in each of the 3 Colleges and one for Professional Service staff . A total of 245 members of staff attended these sessions. Research Roadshows to be continued annually around key themes such as publications, PhD recruitment, grant capture, structural changes internal and external to Bangor. One per College and one for Professional Services. ECI6e Associate PVC Research (REF) and REF Manager working with BU's Athena Swan Committee to review BU's Equality Impact Assessment for REF 2021 in light of the REF Equality and Diversity Advisory Panel's final report (published in June 2022) and to work closely during next REF period to ensure EDI is embedded in the REF cycle and Environment sections throughout the next REF submission. | yes yes no no no | 05/23 02/23 and 02/25 (in prepation fo our 25 submission) early 2024 annually ongoing through REF cycle | ASRCM (HR) RDCG HR PVC Research & Innovation Associate PVC/REF Manager/ASRCM | ECI6a: Response rate to CEDARS 2023 is 30% or above. ECI6b+d: CEDARS 2023: 80% agree they feel part of their research environment/group ECI6e: closer alignment of REF and EDI agendas will ensure EDI considerations are embedded throughout the REF cycle and as such embedded in the ongoing development of the Environment sections for the next REF. | Concordat Survey 2022: - 70% agree or strongly agreed that they feel part of their School's research community - 51% feel they are part of BU's research community. Agreement is much lower for research-only compared to T&R staff: 55% v 81% - School Research Community; 39% v 60% BU Research Community. Future staff surveys/consultations will also need to consider the newly-established College research institutes and ensure that researchers at all levels of seniority feel part of the research community.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | ECR1a ECRS will be invited to regular "Concordat Reflection and Review" meetings, to be held every 6 months. This will allow ECRs to continually feed into Concordat AP implementation ECR1b The School of Ocean Sciences and the School of Medical & Health Sciences have active ECR networks. Example of best practice include ECR Conferences organised by the Health & Medical Sciences ECR network and the School of Ocean Sciences Microsoft Yammer group. Ensure best practice is disseminated to other Schools via RDCG reps, Institute Directors etc. and facilitate pan-University networking of ECRs | no yes | every 6 months from 01/23 from 01/23 | ASRCM RDCG Reps/ASRCM | ECR1a Bi-annual sessions are hosted; these will be in person where possible to facilitate networking. CEDARS 2023: minimum 80% of respondents are aware of Concordat (see ECI1a+d above) ECR1b restart pre-pandemic University-wide, in-person ECR events to run alongside School-level initiatives in order to increase feeling of belonging to wider University research community. | Concordat survey 2022: while 60% of T&R staff felt integrated in BU research communitity, only 39% of research -only staff did.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working. BU published its first Health and Wellbeing Strategy in December 2021 drawing on sector best practice from the UK Healthy Universities Network, the NHS Confederation’s Five Ways to Wellbeing evidence-based guidance, and the Welsh Government’s Wellbeing of Future Generations (Wales) Act. Following the appointment of an Associate PVC for Health & Well-being, a Health and Wellbeing Project Manager and a Health and Wellbeing Project co-ordinator were appointed in May 2022 to develop this agenda and improve support for staff and students across the University. Health and Well-being consultation with over 50 staff members across six focus groups was used to benchmark and identify areas that staff felt would benefit from additional support. Results from the Staff Survey 2022 showed that 56% of respondents (across all staff groups) believed BU cares about staff's mental health & well-being. A total of 123 staff (including BU's Executive team) completed the i-act training (accredited by the Royal College of Psychiatrists) in 2021. 17 of those who completed the training are T&R staff. This training provides practical guidance in terms of understanding and managing mental health and wellbeing in the workplace. As part of the Health and Wellbeing strategy and in order to promote a culture where individual's health and well-being is fostered, BU ran its first Health and Wellbeing Development Afternoon in March 2022. Staff were encouraged to engage in an activity to support their own health and wellbeing, with a number of institutionally arranged actives (such as Mindfulness meditation, exercise classes etc) on offer. The Doctoral School offers training workshops to support managing working relationships, team working, resilience, and motivation. The Doctoral School plays an important role in terms of mediation and pastoral support for PGRs (this represents 40% of Doctoral School staff time). There is a well-established, active PGR rep. network at BU. PGR reps sit on the relevant Doctoral School committee ensuring the PGR voice is heard. The SU engage with PGRs, and have an active PGR society which offers support and social opportunities (weekly ‘Ph Tea’ sessions for example). BU student support services are flagged for all PGRs at inductions and PGRs are directed to these by their supervisors as required.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Research Staff ECI3a A varied programme of events promoting health and well being will be offered during 22/23. ECI3b A new PDR form has been developed that includes an optional question about health and wellbeing and work load. This was published, along with explanatory notes and guidance for managers, online in July 2022. Post implementation further, discussion will be held on how the revised form will be evaluated, specifically as the HBW questions are optional.(see also ECI4) ECI3c - Wellbeing tariffs will be included within the Workload Allocation Model (WAM) to promote health and wellbeing amongst staff. This will involve giving staff a set amount of time within a year to pursue activities which positively impact their wellbeing. Wellbeing Champion and Wellbeing Coach tariffs will be included as leadership and administrative roles within the WAM in recognition of their contribution to employee health and wellbeing. A contingency tariff will be introduced to support the management of unplanned work and unplanned leave. ECI3d Implementation of clear guidance to offer a template of a healthy workload to avoid over-allocation, including a total number of allocable hours for each individual and the proportion of time which should be allocated to Teaching, Research and Impact and Wider Contribution. PGRs ECI3e The Doctoral Schools is working on a pan-Wales PGR wellbeing initiative that will allow the sharing of resources and the establishment of supportive networks across Wales. The Doctoral School has received funding to pioneer a study in PGR well-being at Bangor with a view to raising awareness services and addressing any gaps in provision identified. The Doctoral School is requesting additional institutional questions concerning postgraduate well-being to be added to the annual PRES. The Doctoral School continues to work with PGR-related members of staff and the student union to ensure that well-being provision is constantly reviewed and updated. | no no no no no | 22/23 from 08/22 10/22 10/22 12/22 | HWB Project Manager HR/HWB Project Manager WAM Manager (HR) WAM Manager (HR) DS Manager | . ECI3a+b Staff survey 2024 shows that at least 65% staff agree BU cares about mental health and well-being. CEDARS 2023:at least 65% of those with management responsibility are confident in their ability to respond to any issues relating to health and wellbeing ECI3c Well-being tariffs included in WAM. Tariffs are reviwed after year 1 and reported to the WAM Group. ECI3d Guidance published and implemented. CEDARS 2023/25: at least 65% agree that they are treated fairly in relation to workload. ECI3e PGRs report feeling well supported in their well-being (eg PRES results). | CEDARS 2023 will be too soon to measure full impact of the actions around WAM as full implementation not expected to be completed until 23/24. These will be ongoing and taken forward into next AP.
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | ECI4a PIs/Managers of Researchers will be encouraged to attend HR training sessions such as Managing Wellbeing (reviewed during pandemic) and to complete the i-act course. A feedback session with those who have already completed the i-act training will take place in August 2022 to evaluate the programme and look into the possibility of "train the trainers" to be able to offer i-act training in-house. A number of other course that have "wellbeing components" are available on the Staff Development, for example Absence Management, Having Difficult Conversations. | no | ongoing | HR/HWB Project Manager | ECI4a Once ECI1b completed, data will be collated on training uptake by PIs/Research managers. | The Bangor Manager programme was launched in 21/22 (see EI4)
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | ECM3a As part of the Wellbeing Strategy, work is progressing to establish a network of Wellbeing Champions in each Academic School and Professional Service with an aim of having this support available for September 2022. HWB Champions will play a key role in relaying updates about wellbeing support, organising local wellbeing activities, and ensuring wellbeing is on the agenda in each School/ department. In addition, a group of 21 staff from across the University are currently undertaking wellbeing coaching training which will enable them to offer 1:1 support to individuals who wish to explore wellbeing-related matters. ECM3b PGR well-being champions are being recruited and will work together with the Doctoral School and with the wider BU well-being champion cohort, and report to the Doctoral School committees, throughout the academic year. | no no | 09/22 09/22 | HWB Project Manager/ HR HWB Project Manager/ DS Manager | ECM3a+b: A network of Well-being Champions is established; T&R, research-only staff and PGRs are represented and the network is diverse in terms of gender and other characteristics. Staff survey 2024 shows that at least 65% staff agree BU cares about mental health and well-being. | Feedback via ECRs on RDCG suggests that workload is an issue and that researchers don't feel they have capacity to take on HWB Champion role. It was also noted that women are over-represented on this agenda and the University should ensure men and women are taking on these additional roles. We continue to encourage ECRs to provide qualitative feedback/data via fora such as College Researcj committees, RDCG representatives, focus groups etc.
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | ECM4a The implementation of the University's Dynamic Working framework and principles has provided greater flexibility to many staff members in their work/life balance. A number of resources have been developed, including guidance on how Dynamic Working differs to a scenario where a flexible working application may be more appropriate. Update the Guide to the Employment of Research staff to include links to/information on the Dynamic Working framework, as well as the Flexible Working policy. The Dynamic Working framework will be reviewed early 2023. | no | 03/23 | HR | ECM4a: CEDARS 2023: at least 65% of those with line-management responsibilities for researchers are confident about their ability to manage requests for flexible working appropriately (we cannot provide a baseline as BU did not take part in CEDARS 2021, Concordat Survey 2022: 73% of research-only and 68% of research-only staff strongly agree/agree that they are treated fairly with other groups of staff in relation to requests for flexible working) | Research Staff Feedback via RDGC reps during pandemic suggested that some researchers felt unsupported by their PIs during homeworking. See Actions ECR3a/b below Doctoral School Research hours for PGRs are often regulated for funded PGRs by research councils. However, for those not governed by funder regulations, the Doctoral School has overseen a change in BU PGR regulations so that PGRs can now move freely between part-time and full-time as their circumstances change
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | ECR3a Informal networking and HWB signposting session to be offered to researchers, particularly aimed at ECRs. HWB resources and initiatives flagged in Researcher Inductions (see Actions EI2a+b) ECR3b Focus group on "Experience of Dynamic working" to be held, aimed in particular at ECRs Researchers will be encouraged to complete the new HWB section in their PDRs (see ECI3b). | no no | 03/23 11/22 | HWB Project Manager /ASRC Manager ASRC Manager/ ECR/CRS Reps | ECR3a: awareness of BU's Health & Well-being agenda and support amongst research staff. CEDARS 2023: at least 65% agree that BU actively promotes the importance of good mental health and wellbeing of staff; and that their working environment supports their mental health and wellbeing. ECR3b Focus group on "Experience of Dynamic working" held. Findings and recommendations shared with RDCG and HR Strategy Group. Continually reviewed to ensure research staff feel supported and treated equitably in relation to the rest of University community. | A focus group with research-only staff on "Experience of remote working during Covid" found that many felt isolated during this period and that University communication around returning to Campus tended to focus on students and student-facing staff.
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents. As a Research-intense University, we are sensitive to the power imbalance inherent in the early career researcher and staff-supervisor relationships and are committed to building a zero tolerance research culture where any type of discrimination, harassment, bullying, favouritism, or coercion is unacceptable. We expect all staff to act with the highest standards of professional behaviour during all interactions on and off campus (e.g. at conferences and during field trips). Sexual harassment of female staff and students on research field trips has been raised as an issue by colleagues in our College of Engineering and Environmental Sciences and improving our training in prevention, as well as ensuring our relevant policies and procedures (e.g. Risk Assessment, Due diligence etc) are fit for purpose is a priority. The Conservation research group in the School of Natural Sciences has adopted a "Responsible Researcher" Code of Conduct that sets out the group's values and expectations around integrity and accountability, objectivity, honesty and transparency, inclusivity and collaboration, and leadership. We are building on best practice developed by Student Services (following the 2016 publication by UUK "Changing the Culture - Report of the Universities UK Taskforce examining violence against women, harassment and hate crime affecting university students") such as the training on "Responding to Disclosures of Sexual Violence" for student-facing staff, Bystander Intervention Training (funded by HEFCW) for all 1st year UG students during 21/22 and the recent publication of Sexual Violence and Harassment Support Strategy. Every PGR is allocated a personal tutor with a specific role of offering pastoral support. PGRs are made aware of the processes for grievance and complaints and The Doctoral School engages with any flagged PGR grievance cases. The SU provides neutral mediation and advice for PGRs. The Doctoral School has recently introduced a PGR exit questionnaire to garner feedback from PGRs withdrawing / completing.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | ECI3a BU's Dignity at Work and Study Policy is currently being reviewed following UUK's publication of guidance on Staff on student Sexual misconduct. The revised policy will include strengthened guidance on expected behaviours and conduct on field trips (see above). Following consultation with the Unions, the new policy will be published at the beginning of the 22/23 academic year. Along side this, we are looking to adopt best practice at University level in regards to developing a Code of Conduct for Researchers. ECI3b A "Support & Report" web form for staff will be launched along with new policy. This forms allows staff to report any form of sexual violence, harassment, hate crime, racism or any other related experience that they find unacceptable to members of staff in HR. Issue can also be reported anonymously via this form. The effectiveness and use of the form will be reviewed in 12 months. ECI3c Ensure staff are aware of the revised Dignity at Work and Study Policy and the "Report and Support" form. In the Staff Survey 2022, 65% of respondents indicated they were aware of the current policy. ECI3d Online training module for those organising fieldtrips and those going on field trips is currently being developed; ensuring EDI considerations are embedded in the risk assessment and due diligence processes. ECI3e Following the successful delivery of Bystander Intervention training to all 1st year UG students during 21/22, this training is being rolled out to staff in July 2022. Data to be collated on uptake by research-only and T&R staff. | no no no no no | 09/22 09/22 03/23 10/22 09/22 | APVC Diversity & Inclusion Equality Officer (HR) ASRCM (HR) E&D Officer (Student Services) | ECI3a-c: Revised Dignity & Work and Study policy and "Support & Report" form launched. Staff Survey 2024: increase in awareness of Dignity at Work and Study policy - 75% of respondents aware CEDARS 2023: at least 65% of respondents are familiar with BU mechanisms to report bullying or harassment [no baseline] ECI3d: The actions to develop training and a code of conduct will be evaluated via follow up focus groups. Female staff report feeling more supported and experience a more inclusive, supportive culture on field trips. ECI3e: Data on uptake of Bystander training by research-only and T&R staff collated. Follow up with E&D Officer (Students) to scope further provision for staff. | A foucus group was held in early 2022 to discuss the issue of sexual harrassement of female researchers on field trips. Participants stressed the importance of otraining focusing on prevention of sexual harrassment and strong signalling of zero tollerance to bullying and harrassment at all levels of the University.
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | Managers of researchers/PIs to be encouraged to adopt Code of Conduct for Researchers in their research groups (see ECI3a)
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | ECR4a - Student Services has developed training on "Responding to Disclosures of Sexual Violence" which all student-facing academic and support staff are strongly encouraged to complete. However, many post-docs/CRS supervise or co-supervise UG, Master and PhD students and would benefit from this training. Work with Student Services to make this training available to research-only staff. ECR4b Training on Preventing Sexual Harassment on Field trips is currently being developed (see ECI3d) ; ensure researchers who go on fieldtrips are aware of this and complete the training. Highlight Bystander Intervention training to researcher (see ECI3e). | no no | 06/23 10/22 | APVC Diversity & Inclusion Equality Officer (HR) ASRCM (HR) E&D Officer (Student Services) | ECR4a: At least 20 research staff involved in supervising students complete the "Responding to Disclosures of Sexual Violence" training each academic year. Positive feedback via the training evaluation form at least 80% of research staff who complete the training. ECR4b: Academic Schools engaged in research field trips ensure their staff/students are aware of the training and the requirement to complete the training before taking part in field trips. ECR4a+b: CEDARS 2023: at least 65% agree they would feel comfortable reporting an incident of bullying or harassment; and trust that BU will investigate any reported incident of bullying and harassment fairly.
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion. To ensure an equal, diverse and inclusive culture in the University we have a Strategic Equality Plan (SEP) 2020-24, an associated action plan, formal groups and networks that support the embedding of equality in the University. The SEP sets out our commitment to providing the highest quality, sustainable environment for employment, research and study and to ensuring the wellbeing of our staff and students. We understand that our activities have economic, social, environmental and cultural impacts and that sustainable development is the process of improving well-being in all four aspects in accordance with the Well-being of Future Generations Act (Wales) 2015. BU is committed to embedding EDI into our policies, practices and culture. BU holds an Institutional Athena Swan Bronze award and are working towards a Silver award in 2023. BU has signed up to Advance HE's Race Equality Charter. The greater emphasis on EDI and improving research culture from UK funders (e.g. Wellcome Trust's 2020 report on research culture ) as well as the greater emphasis on "Environment" in REF 2021 is helping push this agenda forward across the sector. Senior HR Equality Officer supports managers/staff when Equality impact assessments need to be carried out and provides any equality-related data that managers may request. HR are currently recruiting to an additional Equality Officer post to support this agenda. Each School has an academic Equality lead and each College has an Equality Committee. The School of Natural Sciences has just launched its Equality Network. 64% of current Concordat staff have completed the online Equality & Diversity training; completion is lower for research-only (49%) than T&R staff (76%). 44% have completed the online Unconscious Bias training (same proportion of T&R and research staff have completed it); 56 have completed the Equality for Managers training (50 T&R/ 6 Research-only). IRIS BU's internal demand management processes (ratified in line with UKRI guidance) have recently been adapted to strengthen EDI considerations in the accessibility and decision-making processes for funding opportunities in Bangor. For internal applications, we are committed to embedding diversity and inclusivity in decision making process by incorporating additional stages in advertising the rolling out of funding process and by ensuring broad representation both in terms of career stage and disciplines on our decision-making panels. University EDI representatives are now always included or referred to for all of our processes. General processes are reviewed annually but a scheme-by-scheme review is now taken, rather than apply a blanket approach. For example, for Round 7 of the UKRI Future Leaders Fellowship scheme we are embedding two early formative stages for potential applicants to ensure that they are fully briefed and aware of the requirements of the scheme before submitting any applications for formal review.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | ECM1a Ensure managers of researchers and researchers complete the online Equality and Unconscious Bias training; research managers to encourage completion in the research groups. Completion to be reported annually (see PCDI6) ECM1b Ensure all PIs/managers of researches complete Equality for Managers training (see also Action EC1Ib). | yes yes | 08/23 08/23 | HR HR | ECM1a: 80% of Concordat staff to have completed online Equality Training and 60% to have completed UB training by January 2025. ECM1b: Only 18% of those on T&R contracts have completed "Equality for Managers" training. Following implementation of ECI1b we will have a baseline of completion by managers of researchers. At least 50% of Research managers to have completed the training by January 2025.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | ECR2a "Equality for researchers and academics" workshop being developed. This will be jointly delivered by APVC Diversity & Inclusion, Deputy Director IRIS and ASRM and will cover an overview of the Concordat and the Athena Swan Charter, what being a "responsible researcher leader " means in the context of BU's commitment to the Concordat and Athena Swan and an overview of /reflection on the requirements from funders to evidence commitment to and progress on EDI See also Action ECI2b and ECI6e. | no | September 2022, annually at beginning of each academic year | APVC Diveristy & Inclusion IRIS HR | ECR2a: Annual "EDI for Researchers" session offered; greater engagement of Concordat audience in EDI agenda evidenced by uptake of training. At least 20 T&R and research-only staff attendance (on average) at each EDI session. Positive evaluation with at least 80% of research staff attendees indicating they found the session useful. | See also ECI6e that will more closely align the REF and EDI agendas at BU.
Research integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity and are able to report infringements or misconduct. BU recognises the importance of maintaining the highest standards of research integrity and therefore complies with the Universities UK Concordat to Support Research Integrity. This Concordat seeks to provide a comprehensive national framework for good research conduct and its governance. An Associate PVC Research Governance and a Research Governance Officer (Governance Services) have recently been appointed to move this agenda forward. Our Concordat Survey 2022 showed that 21% of respondents had some understanding of the Concordat and a further 44% were aware of it. BU has purchased Epigeum software to deliver Research Integrity and Research Ethics training over the next 3 years. Welsh language provisions are currently being discussed with Epigeum with a view to offering as much of the training as possible bi-lingually.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | IRIS ECI5a PVC Research & Innovation has made a commitment to investigating Responsible Research metrics. A paper on Responsible Research Metrics will be considered by BU's Research Strategy Group in August 2022.The San Francisco Declaration on Research Assessment (DORA) and Leiden Manifesto will be assessed and a decision will be made. Governance ECI5b New Research Integrity policy is being developed and will be signed off by Senate in September 2022 ECI5c Software purchased by end of July 2022; Set up by September 2022; Training will be offered via Blackboard to research staff and PGRs to be offered from October 2022 ECI5d Research Integrity Champions to be appointed in each School. Champions will be allocated 1 day/month into promote RI, deliver sessions to Schools on the RI policy and signpost to Epigeum training ECI5e A dedicated Research Integrity webpage is being developed | yes no no no no | 01/25 09/22 10/22 02/23 02/23 | PVC Research & Innovation/ IRIS APVC Research Governance/ Research Integrity Officer (Governance Services) | ECI5a: BU will have decided on an approach to responsible metrics and begun to embed this by end of award period. This will be on ongoing action and impact will be measured in the next AP. ECI5b-e: CEDARS 2023: 75% of respondents are aware of Concordat to Support Research Integrity (40% have some understanding; another 35% have heard of it) CEDARS 2023: at least 50% of respondents are familiar with BU's mechanisms to report incidents of misconduct in relation to research integrity [no baseline] | CEDARS 2023 will be too soon to measure full impact of the actions around RI. These will be ongoing and taken forward into next AP.
ECM3 | Ensure managers report and address incidents of poor research integrity. | This will be addressed in the new RI policy (see ECI5b) which will include guidance on process if something does warrant investigation; RI Panels will be set up for investigating allegations of research misconduct; to ensure transparency, the Panel will have at least one external member who is not affiliated to the University. Named persons and Annual Statement on Research Integrity are already available on Research Integrity/Research Ethics webpage in line with UKRIO guidelines.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | IRIS staff review funder policy and perform due diligence checks on partners at the preaward and postaward stages as appropriate. If there are any major reputational or financial concerns then it is escalated to the Governance team. ECR2a IRIS/Governance to establish a clear workflow around funding proposal, due diligence and research integrity. Action to include review of sector-wide approach to due diligence checks and whether Ethics committees review proposals at pre-award stage or once awarded. The aim would be to implement a light touch process commensurate to the research being proposed and assessment of risk in order that all relevant departments are aware of what research is being proposed. | no | 02/23; following pilot to be launched ahead of 23/34 | Research Integrity Officer (Governance), Deputy Director IRIS | ECR2a: Cross-department (Governance/IRIS) workflow around funding proposal, due diligence and research integrity implemented. The impact of this joined up working will be improved communication between those supporting researchers and in turn improved support for researchers at BU.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | as above |  |  | as above
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution. Research staff feed into policy development via University level committees and groups such as the Senate, the Research Strategy Group, the Researcher Development & Concordat Group. There are regular Deans of College and Heads of Schools meetings. Research staff are also represented on College-level Research Committees and College Equality Committees. Academic Schools hold research away days. You & our strategy - presentations on draft strategies were held and were open to all staff; staff were invited to provided comments/feedback on the strategies. The University’s You & our Strategy development afternoon series provides an opportunity for staff to attend sessions, and engage in discussions on key strategic issues and developments across the University. We have not identified further specific actions under these obligations, We will continue to offer and develop these opportunities. See actions ECI2a on policy development.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making.
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution.
EM5 | Engage with opportunities to contribute to relevant policy development within their institution.
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community.
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation. Under BU's Recruitment & Selection policy staff are recruited based on objective criteria that is fair and equitable and free from bias. HR has recently developed a number of guides to supplement the existing Recruitment & Selection Policies and Procedures. Required composition of interview panels varies according to the post being recruited. However, for all panels at least one staff member must have attended Recruitment and Selection training and the Chair must ensure a diversity of representation on Panels (e.g. at least one member of any interview Panel must be a man / woman if there is a majority of one gender.) There is no longer a requirement for HR to be on all interview panels; this allows research managers (and other chairs of selection panels) more flexibility and autonomy in the recruitment and selection process. HR are on hand to support at every step of the process. BU is currently in the process of acquiring iTrent, a fully integrated HR and payroll system. In terms of recruitment, this will allow us to modernise our approach to recruitment and the recruitment process itself. For example, after an applicant has accepted an offer, and before their first day, they will have access to a ‘onboarding portal’ where information, videos etc can be posted so that new members of staff can start to familiarise themselves before they start (should they wish to). Recruitment & Selection training (which has been offered online since Covid) has been updated to reflect the above. 89 staff of those included in the Concordat audience have completed Recruitment & Selection training (73 T&R/ 16 Research-only) University Staff Inductions moved online during Covid and is now available via Blackboard. All new staff are sent details of the induction procedures relevant to their role in the joining letter accompanying their contract of employment. From September 2022, there will be a hybrid University Induction where new staff still complete the mandatory induction online but this will be supplemented with in-person "Welcome to BU" events to be held every 2 months to give new members of staff the opportunity to network and to meet members of the senior team. Researcher Inductions are currently held twice a year. These are led by PVC Research & Innovation and the Director of IRIS, and feature presentations by key individuals across the University supporting research and researchers including IRIS, HR, Doctoral School, Digital Services, and Governance. During Covid these were held online but will move to in-person again from September (with the option of joining remotely).
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | EI1a Ensure all PIs/managers of researchers complete Recruitment & Selection training (see also Action ECI1b). EI1b Explore the possibility of identiying researcher specific feedback from questionnaire sent to those applying for posts at BU. The candidate feedback data currently received doesn't give a breakdown by type of post applied for. EI1c In the event of a single-gender shortlist, we will encourage shortlisting panels to review the applications of all candidates to ensure no candidates were overlooked. EI1d BU's has adopted best practice in offering posts and roles as flexible/part-time/job-share opportunities. This has been added to the template for all job descriptions and HR will work closely with recruiting managers to ensure these opportunities are included. We will monitor the proportion (and types) of vacancies advertised where this was included as well as how many new staff take on roles on a part-time/job share basis. | yes no no no | following implemention of ECI1b) 06/23 ongoing; ongoing, reviewed at end of each academic year | HR | EI1a: 80% of Research Managers to have completed Recruitment & Selection training by end of 23/24 (following implementation of ECI1b). CEDARS: at least 65% of respondents agree they are confident in their ability to use inclusive, equitable and transparent recruitment processes. EI1b: Feedback from those applying for research positions collated and used to inform implentation of iTrent recruitment processes. EI1c: Process in place to flag any single gender shortlists. Since implmentation there haven't been any single gender shortlists in situation where applications have been received from mixed gender. Continue to monitor and to review how many were amended following review of applications. EI1d: System in place to monitor roles taken up as part-time and job share basis. Many research-only staff (in particular women) work part-time; we are keen to see the option of job sharing explored for research position.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | EI2a ASRCM to attend future "Welcome to BU" events to informally meet and greet new T&R and Research-only staff and signpost to available support, upcoming Researcher Inductions etc EI2b Use the "onboarding" functionality in iTrent to share relevant information/document with new T&R and Research-only staff before they take up new roles; in particular to highlight Concordat and BU's commitment. | no no | from 22/23 04/23 | ASRCM (HR) HR | EI2a+b: CEDARS 2023: 65% of respondents agree that they found the University-level inductions very useful/ useful. [note this covers general staff and Researcher Induction). At least 65% are aware of the support BU provides for their career and professional development. | Online evaluations of recent Researcher Induction sessions showed that they were positively evaluatued with 72% of those who provided feedback indicating excellent or good overall enjoyment of the session and 100% rating the speakers as good or excellent. 81% of feedback rated the session as useful
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression. The University is nearing the final stages of negotiation with UCU on revised promotion criteria for its academic staff which will provide clear and transparent merit-based recognition to staff applying for promotion. It is hoped that these will be available to staff in the next academic year. The University is committed to promoting equality of opportunity in all its activities and aims to provide a work, learning, research, and teaching environment free from discrimination and unfair treatment. The revised promotion criteria will allow applicants the opportunity to draw to the promotion panel's attention any employment or contractual status (e.g. part-time, job sharing etc) and personal circumstances (e.g. maternity, paternity, adoption, parental leave etc) that may have impacted on their career and these will be taken into account in assessing the volume of activity (not quality).
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | EI3a Revised promotion criteria and process implemented; evaluated after first round. EI3b Review the regrading process for research-only staff. Update Guide to the Management and Employment of Contract Research Staff (see EI1c) accordingly to ensure those managing research staff are able to give appropriate guidance. | yes no | 09/23 09/23 | HR HR | EI3a: Staff Survey 2024: minimum 50% academic staff agree that there is a fair and transparent system across the University for promotion" EI3b: Research-only staff have a better understanding of promotion processes and opportunities, in particular BU's regrading process. This will be assessed via surveys (note that CEDARS 2023 will be too soon measure impact of this) as well as via discussions with ECRs in focus groups. | BU's promotion process has been undergoing a review and promotions have been on hold during the review. The lack of promotion opportunities has therefore been an issue for staff. In the Staff Survey 2022, 70% either disagreed or "neither agree/nor disagree" that there is a " fair and transparent system across the University for promotion". Lack of clarity around promotion process and opportunities was also raised in consultation with ECRs. Researchers were not clear on what promotion opportunities there were for staff on fixed-term research contracts and many were not aware of BU's regrading process. This was also reflected in the Concordat Survey 2022: whilst 60% of T&R respondents agreed that they were treated equally with other groups of staff in relation to career progression and promotion, only 32% of research-only staff agreed.
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers.
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities. Relevant legislation underpins aspects of BU's Mangers training such as Recruitment & Selection and Absence Management training. Equality for Managers as well as the mandatory online Equality training is underpinned by our Public Sector Equality Duty requirements, which are to eliminate unlawful discrimination, harassment and victimisation; advance equality of opportunity between people who share a characteristic and those who don't; and foster good relations between people who share a characteristic and those who don't. A Bangor Manager Guide that includes key contacts and information about relevant support and training is sent to all new managers (but see Action ECI1e re identification of Managers of Researchers).
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | See ECI2a+b for proccesses relating to grant funding .
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | ER1a Ensure Researchers are provided with the relevant information at School Induction and project level induction. See ECI2a+b for proccesses relating to grant funding . | no | ongoing | DoR/ Managers of Researchers | ER1a: CEDARS 2023: minimum 60% agree induction at institution level, School level and Local induction relevent to role was very useful/useful [no baseline data available]
ER2 | Researchers understand their reporting obligations and responsibilities. | See ECI2a+b for proccesses relating to grant funding .
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews. Line management training is provided by Staff Development HR via a number or programmes/sessions. The Bangor Manager Programme launched in 21/22 and is aimed at staff new to the University as well as existing members of staff who have recently taken on (line) management duties. The programme consist of 12 workshops: An Introduction to Managing People, Equality and Diversity for Managers, Developing Performance Management Skills, Recruitment and Selection Training, Undertaking Effective Performance Development Reviews (PDRs), Managing Sickness Absence, Coaching Skills for Managers, An introduction to Change Management, Managing in a Bilingual Environment, Having Difficult Conversations, Understanding Self and Others, Wellbeing related workshops such as Mental Health First Aid Training or i-act Training (see ECI4). There are currently 27 staff enrolled; none of whom are T&R/research staff which suggests that the programme may be perceived as too general/not relevant for managers of research staff and/or staff don't have the time to commit. Note that staff can also sign up to individual sessions without registering for the Bangor Manger Programme (number of T&R Concordat staff who have completed Equality for Manager and Recruitment & Selection given above in section on EDI). Bangor managers have access to ACAS (Advisory, Conciliation and Arbitration Service) resources via the HR website. This includes online learning modules on topics such as people management. BU's annual Performance Development Review (PDR) process integrates appraisals and career development reviews. The scheme is developmental in approach and provides a space to explore professional development opportunities and identify specific training needs. Completion rate in the last PDR cycle (up to November 2021) was 84% across all staff. 70% of respondents to the 2022 Concordat Survey indicated they had taken part in a PDR in the last 12 months. Research project management training is offered as part of the IRIS Training programme on the Researcher Development Programme.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | EI4a When system in place to identify PIs/managers of researchers (see ECI1b) relevant line-management training to be highlighted via Guide to Management, emails, PDRs etc. Bangor Manager programme to be reviewed in order to identify sessions that are particularly relevant for PIs/Managers of researcher. EI4b We are exploring the provision of bespoke Heads of School training which will be aligned to the People and Talent Strategy. The Heads of School training programme will be run by the end of 22/23 academic year. EI4c Training for PIs/Research Managers on conducting PDRs with contract research staff to be developed for next PDR cycle. This is in particular fous on strengthening the "career development review" element. Project management training provided by IRIS within core module 2 "Managing Research Projects" (see Actions PCDI1) | no no no | 04/23 07/23 01/23 | HR Director HR Deputy Directorr HR/ ASRCM (HR) | EI4a+c: Once ECI1b completed, data will be collated on uptake of line-management training by PIs/Research managers (see also ECM1a). Responses to CEDAR show that those managing researchers are confident in their ability to manage appraisal/review processes effectively; and to provide effective feedback to individual researchers EI4b: Heads of Schools have completed bespoke training. EI4c: Positive feedback from research-only staff (particulalry ECRs) that PDRs included a helpful discussion around career development and planning.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | EI5a The WAM system pilot phase will be completed by conducting a review of all draft tariffs and engaging with Schools, academic staff and unions on the suitability and accuracy of these tariffs. For T&R staff this will include establishing a specific Research allowance tariff for Research activities. EI5b Following the review, the WAM system will be extended to all nine of the University’s Schools to achieve workload equity, transparency and fairness. The WAM will be evaluated following the wider roll-out. Regular reviews (every two years) will also be conducted to ensure the model is current and accurate and to implement improvements. EI5c Aligning the WAM system with the PDR process with regards to the timing of publishing workloads, to evidence and inform discussions around workload, performance and planning. ECI5d While staff who have externally funded research only fixed term contracts are not included in the University WAM, guidance will be developed for PIs and research managers to ensure that workloads of all research only staff are equitable and reasonable. | no no no no | 09/22 04/23 09/23 09/22 | WAM Manager (HR), WAM Task group | EI5a-c: WAM to be reviewed every two years to ensure the model is current and accurate and to implement improvements. ECI5d: Feedback from consultation with ECRs suggests that workload is an issue for this group of staff (not included in WAM). In particular concerns were raised regarding researchers on fixed-term contracts being expected to apply for their own funding without much support being offered. Impact of guidance around workload for research-only staff measured via ongoing consultations with researchers.
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | see EI4
EM4 | Managers actively engage in regular constructive performance management with their researchers. | see EI4
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | [5 empty] | Concordat Survey 2022: 70% have taken part in a PDR in the last 12 months (T&R 72%; Research-only 67.5%). Whereas 59.5% of T&R staff rated it "overall very useful/useful" only 44% of research-only staff did. 47.5% of research-only staff (and 44% of T&R) respondents rated their PDR as very useful/useful in leading to training or other continuing professional development opportunities. Feedback from consultation with ECRs suggests that while generally their experiences of PDRs were positive, many felt that the challenges of being on a fixed-term contract often made the forward planning/career development aspect difficult. Following roll out of training (EI4c), at least 60% of research-only staff answering CEDARS 2023 rate PDR very useful/useful.
Job security
The aim of this obligation is to improve the job security of researchers. The Anti-Casualisation Group, a joint working group with representation from HR and Campus Unions, was established in early 2020 to look at “casualisation of employment” (including the issue of use of fixed-term contracts), reflecting the discussion of issues at national level on matters such as phasing out zero hour contracts, converting hourly paid staff to fractional contracts, and setting up bridging funds. The overall aim of the group is to reduce the number of staff on fixed-term contracts to provide security of employment. As such, BU's Fixed-term contract policy has also been discussed by the group; it is one of a number of policies that are part of the University's Ordinances exercise. (In August 2020 Bangor University Court approved a new Charter, which has now been approved by the Queen in Privy Council. The new Charter will be implemented in or around September 2022. At the adoption of the new Charter, the existing Charter and all associated Statutes and Ordinances will cease to have effect. As part of these changes, a number of HR policies and procedures will no longer apply to staff. The University and the Unions have negotiated a set of HR Ordinances for all staff (with minor consequential changes to contracts) to replace these old rules, policies and procedures. The aim is to have a modern, fit for purpose, set of documents which are compliant with current employment law and which can be kept up-to-date more easily.) A Bridging support scheme was approved by HR Task Group in June 2022. This scheme aims to encourage the retention of experienced and skilled staff and sustain research teams and expertise; avoid the break in employment and career which might otherwise be faced by research staff; and maximise the opportunity for such staff to produce high-quality outputs and/or research impact at the end of funded contracts/grants. The Deputy Director HR (who is a member of the Anti-Casualisation group) attends RDCG meetings twice a year to provide updates on the work of the group and report on progress regarding the implementation of the new fixed-term contract policy and the bridging support scheme.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | EI6a BU's Fixed-term contract policy has been reviewed by the Anti-Casualisation Group. The Policy is underpinned by the Fixed- term workers regulations, which provides a list of objective justifications for the use of fixed term contracts, including a second set of tightened objective justifications where a member of staff has been employed for four years or more. This will enable managers to give greater consideration to the transfer to research staff onto permanent contracts. Final policy to be approved and implemented during 22/23 academic year. EI6b The Bridging Support Scheme forms and guidance are being finalised; to be launched during 22/23 academic year. Raising awareness of its implementation will do be done via communication in Staff Bulletin and emails to HoS/Institute Directors/ Directors of Research/Researchers. Work with comms to ensure researchers and managers of researchers are aware of this support available. The uptake of the scheme will be monitored to ensure equitable application where possible. | no no | 09/22 09/22 | Deputy Director HR Anti-Casualisation Group | EI6a: New policy approved and implemented. Reduction in the number of staff on fixed-term contracts after four year continuous service. EI6b: Following the launch of the Bridging Support Scheme, we will monitor the allocation of bridging funds awarded across the University and review in 12 months time. | Feedback via RDCG survey as well as the consultation with ECRs has highlighted that concerns around fixed-term contracts and (in)security of employment remain key issues for many of research-only staff. Researchers on FTC have raised concerns about feeling pressure to write grants to secure their future employment; some have not felt supported by their PIs/the University.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it. Research Staff Researcher Development Programme is managed by ASRCM and brings together the IRIS Training Programme, session delivered by Digital Services, HR, Corporate Communications etc. It is aligned to Vitae's RDF. Also listed on the Researcher Development programme are research seminar series that are open to researchers from across BU (e.g. Research Seminars STEM and Medicine; Bangor Tech Talks). Researchers are also encouraged to attend sessions offered on the General Staff Development schedule, in particular those focusing on personal effectiveness. Sessions are advertised via email and the Staff Bulletin. PGRs PGRs are encouraged and supported to complete the training and development activity they require, and is relevant to them, to complete their doctoral programme and to move forward with their career. Hence the Doctoral training programme is structured and maps onto the relevant phases of the Doctoral programme. IRIS Training Programme The programme structure is aligned to the Researcher Development Framework (RDF-VITAE). The programme features three core modules: Module 1: Planning and Applying for Research Funds; Module 2: Managing Research Projects; and Module 3 Research Outcomes. This is supplemented further with 'Spotlight' training sessions, for example focusing on ECRs, MCRs, specific funders, grant factory sessions and college, school and research centre specific sessions. Researchers also have an opportunity to engage in informal interactions through the monthly IRIS drop-in sessions. Academics and researchers contribute to the delivery of sessions and this interaction is particularly valuable. The engagement across the programme has been very good. In dialogue directly with researchers and research centre staff, gaps have been identified that are being addressed for the 2022/23 programme of training and they are noted in the actions below. eResearch Training eResearch activities and services are being developed to be able to offer additional training opportunities to staff and PGRs. This growth is intended to align with steady growth in the eResearch team, in the recruitment of additional Research Software Engineers. Details of training being developed are noted in the actions below. The eResearch team will continually assess and reinvent the range of training offered to ensure relevance and, in so doing, to offer capabilities in areas of game-changing new technology such as Artificial Intelligence and Machine Learning. We take a holistic view of CPD which (in addition to the programmes outlined above) includes conference attendance, mentoring/being mentored, coaching, (non-research) training such as that available via the Staff Development Schedule (including Equality training), leadership training (see PCDI4), School and/or College level training and development opportunities.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | PCDI1a Ensure that research staff are aware of BU's training, development, mentoring and coaching opportunities available. PCDI1b Develop through consultation with relevant research groups and Colleges a University Guidance regarding the implementation and the broad range of activity that can be included within 10 days professional development; communicate via Staff Bulletin, include in PDR guidance and Research Manager Guide PCDI1c Work with Schools/Colleges to ensure discipline specific training is offered alongside the centrally-provided more generic training PCDI1d Work with researchers and the wider university professional services to co-produce and deliver training sessions related to enterprise and civic engagement. This will be aligned with both the University Civic Engagement Strategy, the Employability Service and the External Engagement Strategy (as appropriate). PCDI1e Develop through consultation with mid-career researchers a programme of training specific to their needs. In particular, identified areas are: building networks; the transition from co-investigator to principal investigator; and managing grants. PCDI1f Develop module 2 further in relation to managing research projects. This will be in consultation with researchers, colleges, schools, eResearch services and other professional services. Also, develop "Research Outcomes" module (3) further to include sessions on relationship building and public engagement and impact. PCDI1g In consultation with eResearch services and Digital services, create digital resources for researchers to access through the University learning platform (Blackboard). A typical example would be the creation of Panopto, bite-sized information and 'How to...' This is part of our mixed and complementary approach to engagement and access to development sessions and resources. . | no yes no no no no no no no | ongoing 06/23 review at end of 22/23 03/23 10/22 02/23 06/23 develop during 22/23, review in 07/23 ahead of 23/24 roll out. as above | ASRCM ASRCM IRIS IRIS/HR IRIS IRIS IRIS IRIS/ Digital Services/HR eResearch/ Digital Services eResearch/ Digital Services | PCDI1a: CEDARS: At least 65% are aware of the support BU provides for their career and professional development PCD1b: Guidance on the 10 days CPD agreed, incorporated in Guide to managers (see ECI1c), communicated to researchers via Staff Bulletin and PDR guidance. CEDARS 2023: 50% of respondents have spent at least 6 days on CPD. PCDI1c+d: Researchers, Colleges, schools and professional services are proactively engaged in co-producing training sessions 'working together ethos'. Engaging with and building on researchers aspirations at different career stages. Accessible resources and training with sustained support from research leaders. Varied and innovative approaches to engagement evident. PCDI1c-i: Improved and extended Researcher Development Programme offered in 22/23. An online evaluation form was sent out after each 21/22. session. Low response rate - approx.12% across all sessions. Increase response rate to evaluations to 25% in 22/23. | Concordat Survey 2022: 28% of T&R respondents and 24% of research-only respondents indictaed that they had spent 6-10 or 10+ days on traininig and other CPD activties in the last 12 months. 67% of both cohorts had spent 1-5 days on CPD. Close to 40 training session were offered on the Researcher Development Programme during 2021/22 with over 300 attendees across all sessions. Those who did submit evaluations in 21/22 found the sessions very useful with 68% of resondents rating the "Usefulness and relevance of the session" of excellent and a further 25% as good.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | Note: first two actions continuation of PCDI1 PCDI1ih eResearch support to focus on four key technologies: R, Python, Matlab and Supercomputing. We aim to develop and improve course content using input from several sources, including existing material developed under the Supercomputing Wales project, experience from the Software Carpentries movement and existing University-wide efforts. PCDI1i eResearch to grow in-person training and enable staff’s own-pace training through coordination with colleagues from the Digital Services Teaching & Learning team to deploy online content via Blackboard and other tools. Recognising common areas as well as those that require discipline-specific content will require engagement/communication with the three college Research Institutes. PCDI6a The new iTrent system will improve our ability to record, report and monitor training uptake. Following the implementation of the new system (04/23) we annually capture "Concordat" CPD data and report to the RDCG and HR Task Group. | no | from end of 23/24 | HR | PCDI6: Annual CPD report presented to RDCG and HR Strategy Group. Data also shared with researchers via Concordat review meetings (ECR1a) CEDARS 2023: 50% of respondents have spent at least 6 days on CPD, ensuring that staff include all categories of CPD. | Concordat Survey 2022: 28% of T&R respondents and 24% of research-only respondents indictated that they had spent 6-10 or 10+ days on traininig and other CPD activties in the last 12 months. 67% of both cohorts had spent 1-5 days on CPD.
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | PCDM3a: Raise awareness of responsibilities of research managers in particular around allowing time and supporting researchers to engage in CPD (see ECI1b/c); acknowledging challenges to PIs of balance of delivery of research. Ensure this is embedded in PDR (ECI4c). | no | following implementation of ECI1b | HR IRIS Directors of Research | PCDM3a: CEDARS 2023: minimum 60% agree that their manger encourages them to engage in personal and career development activities; at least 60% of those line managing researchers indicate they are confident in their ability to actively support researchers working towards their career aspirations. | Concordat Survey 2022: 78% of research-only staff agree that they are encouraged to engage in personal and career development. However, only 47.5% of research-only staff respondents rated their PDR as very useful/useful in leading to training or other continuing professional development opportunities (see EI4c)
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | PCDR1a: Encourage researchers to keep a record of conference and workshop attendance, engagement in mentoring or coaching activities etc. The new iTrent system will allow staff to check their training records which will make it much easier for staff to keep track of CPD activities. | no | from 09/23 | HR | PCDR1a: Following development and communication of guidance around what should be included in the 10 days CPD (see PCD1b) , iTrent will allow easier collation/monitoring of training/development uptake. | Consultation with ECRs has highlighted that some would appreciate more opportunities to gain teaching experiences, for example by being involved in MSc or PhD Supervision. Variation across School in regard to how much and what kind of teaching research-only staff are currently able to be involved in.
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews. We do not have a seperate process for "career" development reviews, rather career development reviews are integrated into BU's Performance Development Review (PDR) Scheme which is developmental in approach and provides a space to explore professional development opportunities and identify specific training needs. We have a outlined a number of actions to improve our PDR processes and in particular the "career development" discussion of the PDR (ECI4c; ECI3b)
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews.
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually.
PCDR4 | Researchers positively engage in career development reviews with their managers.
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience. The Doctoral School runs a Year three focussed PGR workshop ‘Finishing up and moving on’ that looks at ‘beyond the PhD’ and gives guidance on career options, funding, career and recruitment fairs etc. Doctoral School are identifying relevant PGR support funding to work on online careers resources. A downloadable PDP is available on the Doctoral School website, and is introduced at induction. This provides a skills gap analysis, a mapping of skills onto the RDF, and a structured record to create a skills transcript. This is commonly used to structure the training related discussions with supervisors as well as fuelling career focussed discussions / planning. A link to BU's Handbook for Postgraduate Researchers and Supervisors can be found below (row 117). BU is a member of Vitae and all staff/PGRs have access to Vitae's careers-focussed resources. There are links to the Vitae website from the Doctoral School and the HR Researcher Development website. Bangor University's Employability Team are part of Student Services. The team provides information, resources, advice and guidance to our BU students and graduates, to help develop their employability and confidence, and explore, pursue and realise their career aspirations. The service is mostly UG focused and not closely aligned to Research Strategy and/or People & Talent Strategy.
| Ensure that researchers have access to professional advice on career management, across a breadth of careers. | PCDI3a DS/HR to work with Employability/Careers service to explore the possibility of PGRs and ECR staff having access to/benefitting from professional advice on career management. The Employability team works closely with Employers. Meeting to be held with Employability Manager to discuss possibility of securing resource in order to expand and enhance the support they are able to provide. PCDI3b Vitae support and resources to be more widely showcased via emails, Staff Bulletin, and researcher and PGR inductions. | no no | 09/23 09/23 | HR Doctoral School Employability DS Manager/ ASRC Manager | PCDI3a+b: Researchers are aware of career development support at BU and via the Vitae website. Also ensure that support in this area is linked to funder requirements/developments such as the narrative CVs introduced by the Royal Society (Résumé for Researchers) and UKRI (R4RI).
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications.
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities. The support and development of midcareer researchers is a priority in the current action plan, linking to the priority outlined in the new research strategy around Identifying, developing and retaining future research leaders. Following a successful in-house Research Leadership programme in 2018 and 2019; we ran a pilot joint (online) Researcher Leadership Programme with Aberystwyth in 21/22. 12 participants from each Institution were selected and sessions covered. Feedback was positive with 62.5% of respondents rating the programme overall as "excellent" and a further 25% as "good". Following the completion of the programme, PVC Research & Innovation, Director of HR and Chair of RDCG invited all Bangor participants to an (in-person) end-of-programme disucssion on next step. BU is part of the Welsh Crucible, an award-winning programme of professional and leadership development for the future research leaders of Wales. Thirty researchers from across Wales are selected each year to work together to explore how they can tackle the current research challenges facing Wales, as well as looking at the skills needed to take their research careers to the next level. The programme is open to early and midcareer research (min 6 years of research experiences incl. PhD). The programme is funded by partner institutions (Aberystwyth, Bangor, Cardiff, Swansea and University of South Wales) and HEFCW. BU has committed to another two years following this year's programme. BU is committed to supporting the career and leadership development of female staff. 9 women have been supported to attend Advance HE's Aurora programme since 2020, 3 of whom are T&R lecturers/Senior Lecturers and one is in a senior management position in IRIS. Aurora participants are mentored by Senior female academics through the programme. We are committed to growing the cohort of those who have attended Aurora, and to developing female (research) leaders at BU.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | PCDI4a Following a review of the 21/22 joint Research Leadership Programme in August 2022, look into possibility of running the programme jointly again in 22/23. Alternatively, develop Bangor RLP 22/23. PCDI4b Encourage researchers especially mid-careers researchers, to apply for Welsh Crucible 2023 and 2024. Nominations for a mid-career researcher from each School will be sought via Hos/DoR. PCDI4c University-funded/school funded places on Aurora programme PCDI4d Ensure that completion of leadership training is flagged to HoS/DoR; involve Research Leadership Alumni and Welsh Crucible alumni in delivery of training and development, in particular supporting ECRs. PCDI4e Ensure support is in place following unsuccessful Fellowship, Future Research Leaders etc applications. DoR and IRIS to support applicants to identify different funders/approaches. | yes no no no no | 22/23 01/23 annually ongoing ongoing | PVC R&I, Chair RDCG, ASRCM (HR) PVC RI, DoR, ASRCM (HR) Director HR/ASRC Manager (HR) DoRs/HR DoRs/IRIS | PCDI4a: In-house Research Leadership Programme to run again in 22/23. Programme to feature some of last year's participants to reflect on usefulness of programme and how participants have used what they learned in their research leadership. Evaluation shows that participants rate the programme as good or excellent in line with the evaluation of the 21/22 pilot programme. PCDI4b: Increase in the number of applications from Bangor to the Welsh Crucible programme. 6 Bangor applications for received for the 2022 programme, increase to at least 10 for 2023 and 2024 programme PCDI4c: BU is committed to continuing to support female staff to attend Advance HE's Aurora programme. 5-7 Centrally- and School/Department-funded places to be offered annually. PCDI4d: Those who have completed leadership training are linked with Directors of Research who will support the development of leadership teams in Colleges around emerging research themes. Key that mid-career researchers are given the opportunity to engage in the "bigger picture" and are included in succession planning. HR will ensure that HoS and DoR have a record of who has completed (research) leadership training. PCDI4e: This aligns with changes to the funding landscape requiring a more team based approach to deliver larger projects. | Feedback via online evaluation of RLP 21/22 as well as focus group with participants and PVC Research & Innovation was overall posiitve (see above). However, feedback via the the free-text comments also highlighted the issue that to improve their research leadership abilities participants need to know what the Institutions want them to be better at as a result of taking part. The question of "what next" was also raised in the focus group led by PVC Research & Innovation and Bangor participants.
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours.
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development.
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research. Academic Schools hold Careers and Recruitment fairs; some specifcally for PGRs.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | PCDI5a Working with Wales Concordat network to deliver a series of "Careers beyond academia" sessions featuring researchers who started their careers at Welsh institutions and have since moved into other sectors. This series will give researchers the opportunity to hear about different career trajectories and pathways and will showcase the ways in which BU and other Welsh HEIs contribute to the development of a highly skilled and talented workforce for Wales, the UK and beyond. This will be piloted in 22/23; aim is to deliver four online events, each with three speakers. PCDI5b BU "Career paths for Researchers" panel event to be held once a semester, supported by BU’s PVC Research & Innovation. Working with networks such as BU Alumni, KESS partners and University Council to identify and recruit suitable speakers. Key element is in-person nature of sessions to allow PGRs/ ECRs to network with panellists and other participants. Talks will be recorded to build a bank of career pathway stories, accessible on the Doctoral School and Researcher Development HR websites. | no no | 22/23 10/22 and 04/23 | HR Doctoral School Alumni | PCDI5a+b: Four pan-Wales online sessions and two in-person session at Bangor offered. Recordings made available to researchers. Evaluation of all sessions taken place. ECRs report feeling supported in considering a wide range of future career options within and beyond academia.
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments.
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments.
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Bangor University Strategy 2030 |  |  | APVC | Associate Pro-Vice Chancellor
2 | Research at Bangor University |  |  | ASRCM | Athena Swan & Research Concordat Manager
3 | BU's Health and Wellbeing Strategy 2020-24 |  |  | BU | Bangor University
4 | BU's Equality, Diversity & Inclusion Policy |  |  | CEDARS | Culture, Employment and Development in Academic Research Survey
5 | BU's Recruitment & Selection Policy |  |  | CROS | Careers in Research Online Survey
6 | Bangor Doctoral School |  |  | DoR | Director of Research
7 | BU Handbook for Postgraduate Researchers and Supervisors |  |  | ECR | Early Career Researcher
8 | BU's Doctoral School Personal Development Plan |  |  | EDI | Equality, Diversity & Inclusion
|  |  |  | HoS | Head of School
|  |  |  | HR | Human Resources
|  |  |  | HWB | Health and Well-being
|  |  |  | IRIS | Integrated Research and Impact Support
|  |  |  | MCR | Mid-career Researcher
|  |  |  | PDR | Performance Development Review
|  |  |  | PGR | Postgraduate Researcher
|  |  |  | PVC | Pro Vice-Chancellor
|  |  |  | RDCG | Researcher Development and Concordat Group
|  |  |  | RI | Research Integrity
|  |  |  | RLP | Research Leadership Programme
|  |  |  | T&R | Teaching and Research
|  |  |  | WAM | Workload Allocation Model