## Sheet1
Cynllun Gweithredu HREiR Action Plan (2020-2022)
Details
| Institution name: | Prifysgol Bangor University | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 5 | Audience | # | Comments
| Date of submission: | 2020-07-29 | Research staff | 517 | 205 are CRS and 187 are ECRs (Research Council definintion)
|  |  | Postgraduate researchers | 660 | These are PhD/MRes students
|  |  | Research and teaching staff | 929 | The 517 staff noted above are included in this figure.
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Old Concordat principle and clause
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | a) Produce an annual report of progress in relation to the Concordat Action Plan for the; Executive Team, Council, Senate and staff and send to relevant staff and include in the Staff Bulletin. b) Every two years hold a survey and focus groups to track progress and identify new ideas to support and develop researchers. c) Create a section regarding the Concordat on the Doctoral School webpages and the Doctoral Supervisors webpages. d) Include information about the Concordat in the School induction process. e) Include a section regarding the Concordat in the ‘Bangor Research Manager’ workshop. f) Ensure that the link between University / School Athena SWAN Action Plans and the Concordat are highlighted to ensure that staff understand how both seek to support staff in the University. | I. 80% of staff note they are aware of the: Research Concordat (50%, CROS 2019) II. 50% note they are aware of the HR EiR Award (34% CROS , 2019) (CEDARS) | a) May 2021 b) April 2022 c) Dec 2020 d) Dec 2020 e) Dec 2020 f) Ongoing | a) DDHR(D) b) DDHR(D) c) DS d) HoS e) HRO(SD) f) AS&RCM & UASWG |  |  | New
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | a) A revised version of the’ Bangor Manager‘ Workshop will be introduced in 2020. A specific version for research managers will be also be developed (Bangor Research Manager) that will be more specific to their requirements. This workshop will provide an overview and update of relevant policies and procedures. b) As part of the Bangor Research Manager workshop a web page with key information for managers and links to relevant policies will be developed. c) Review the Guide to the Management and Employment of Contract Research Staff to ensure guidance regarding policies are up to date and in some cases expanded. This will provide the basis for the Bangor Research Manager workshop. d) Communicate the Strategic Equality Plan to all staff. e) Include relevant updates in the Staff Bulletin. | 70% of staff who attend the Bangor Research Manager workshop find it useful. (Programme Evaluation) | a) Dec 2020 b) Dec 2020 c) July 2021 d) Oct 202O e) Ongoing | a) HRO(SD) b) HRO(SD) c) DDHR(D) d) SHRO(Eq) e) DDHR(D) |  |  | P2.1 P6.8
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | WAM a)Introduce the Academic WAM system and provide guidance for research managers regarding managing reasonable workloads and addressing work life balance issues of staff. b)Develop a WAM website to support the project. Health and Wellbeing c) Examine the recommendations of the Health and Wellbeing Group and identify where the recommendations can be integrated into the Concordat Action Plan. d) A member of the RDCG will be invited to represent the views of CRS/ECRs and be the Wellbeing Champion for researchers on the Healthy University Group. e) Include information about health and wellbeing support in local induction as well as the University induction Dignity at Work and Study Policy f) Review the University’s Dignity at Work and Study Policy and consider the Policy in relation to the researcher context and communicate the new policy to researchers. g) Develop a staff guide to equality so that all staff are aware of the equality policy, strategy and all responsibilities to ensure an inclusive and equal University. | Health and Wellbeing I. 60% of research staff believe that their institution actively promotes the importance of health and wellbeing amongst staff (35% CROS, 2019) II. 70% of research staff feel that the University is interested in their health and wellbeing (56% Staff Survey, 2020) III. 50% of research staff note that they are not struggling to cope with the volume of their current workloads (31% Prof/Readers, 34% T&R Lecturing staff, Staff Survey 2020) (RO staff 62%) IV. 60% of research staff believe that their institution actively promotes the importance of health and wellbeing amongst staff (35% CROS, 2019) Equality and Diversity and Dignity at Work and Study Policy I. 90% of research staff think staff at their institution are treated fairly (CEDARS) II. 85% of research staff believe their institution is committed to equality and diversity (75% CROS, 2019) III. 75% of researchers note they are familiar with their institution's mechanisms to reports incidents of discrimination and bullying and harassment (CEDARS) | a) Sept 2021 b) Sept 2020 c) July 2021 d) Dec 2020 e) July 2021 f) Oct 2020 g) Jan 2021 h) Sept 2020 | a) DDHR(D) b) PO(WAM) c) RDCG d) RDCG e) HRO(SD) f) HRO(SD) g) SHRO(Eq) & CEG h) SHRO(Eq) |  |  | P6.9
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | a) Ensure that all research managers have undertaken the; I. On-line equality training II. Unconscious bias training III. Equality for Managers Workshop. b) Review the Recruitment and Selection training to include interviewing skills c) Introduce an on-line workshop for research managers regarding health and wellbeing for researchers Health and Wellbeing d) Send information to managers and staff regarding the health and wellbeing support available to them. This is particularly relevant in the current period with staff working from home. This will continue to be supported by the University and in the Colleges trhough the return to work questionniare and prvision being put in place. | a) I. On-line equality training – 90% of researchers have undertaken the training II. Unconscious bias training – 90% of researchers have undertaken the training III. Equality for Managers Workshop – 90% of research managers have undertaken the training b) Completed c) Completed d) Completed | a) May 2022 b) Dec 2021 c) March 2021 d) Ongoing | a) SRO(Eq) & HoS b) HRO(SD) c) H&WG d) HRO(SD) |  |  | P2.3
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | a) Review the Code of Practice for the Assurance of Academic Integrity and Quality Assurance and review the Code in light of the draft Professional Behaviours Framework to ensure that behaviours in terms of academic integrity and ethics are included. b) Introduce sessions for staff in relation to the Concordat for Research Integrity. c) Review how best to communicate the DORA principles in the University. d) Ensure that the expectations in relation to academic citizenship in the draft academic promotion criteria is communicated effectively in presentations to staff. e) Ensure that research integrity and professional conduct is included in the ‘Bangor Research Manager' workshop and the Research Leadership Programme. f) Expand the Guide to the Management and Employment of Research Staff to include more information about research integrity. | I. 80% of staff note that they are aware of the Concordat to Support Research Integrity, (CEDARS) II. 80% of staff believe that their institution promotes the highest standards of research integrity and conduct, (CEDARS) | a) Dec 2021 b) Dec 2021 c) Jul 2021 d) Dec 2021 e) Dec 2021 f) Dec 2021 | a) PCVRII b) DirRIIO c) RIISG d) DDHR(D)&DirRIIO e) DDHR(D) f) RIIO |  |  | P6.1
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | a) The SCG and RDCG to consider the results of the biennial Staff Survey that will highlight researchers’ responses to montiro progress against specific areas. b) The SCG and RDCG will use the CEDARS to track progress against the KPIs of the Concordat Action Plan. c) To improve overall service to research staff a survey will be held to ask for researchers’ opinions regarding key services e.g. RIIO, Finance, HR, Doctoral School and the Library. d) The ECRs on the RDCG are given specific responsibilities in their roles and a requirement to arrange two events per annum in their Colleges to encourage the development of a research culture and the engagement of research staff. e) To develop a dynamic and supportive research environment that encourages the collaboration create a series of quarterly meetings for all researchers to share ideas to develop a dynamic research culture. f) Continue to develop the University-wide ECR Network to identify training requirements and encourage engagement with the broader research environment in the University. g) Hold two events of the ECR Network during July to early September to maintain contact between the researchers and enable them to meet informally. | I. 80% of staff believe that their institution promotes the highest standards of research integrity and conduct (CEDARS) II. 60% feel that the institution appreciates their contributions to institutional policy and decision making (CEDARS) III. 75% Staff feel included within my immediate research environment / research group (CEDARS) IV. 70% feel valued at work (CEDARS) V. 70% feel they have a good level of job satisfaction (CEDARS) | a) May 2021 b) May 2021 c) May 2022 d) Sept 2020 e) Dec 2021 f) May 2022 g) Sept 2021 and ongoing | a) SCG&RDCG b) SCG&RDCG c) AS&RCM d) RDCG e) PVCRII f) RDCG g)RDCGReps |  |  | P6.10 P7.5
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | [6 empty] | P6.6
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | [6 empty] | New
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | [6 empty] | P6.6
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | a) Ensure that all managers have undertaken the Equality for Managers Workshop. b) Ensure that mangers who are involved in recruitment attend the recruitment and selection training. c) Ensure that all managers have undertaken the unconscious bias training. | I. See success measures in EC13 II. Equality for Managers Workshop – 90% of research managers have undertaken the training III. Recruitment and Selection Workshop – 80% of relevant manager have undertaken the training IV. Unconscious bias training – 90% of managers have undertaken the training | May 2022 | Research Managers |  |  | New
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | a) Ensure that managers receive updates of the Code of Practice for the Assurance of Academic Integrity and Quality Assurance in Research. b) Ensure that managers receive information regarding the Research Ethics Framework. c) Engage with research staff in the development of the Professional Behaviours Framework to ensure that it addresses the ethical behaviours required of researchers d) Research managers will be required attend the sessions regarding the Professional Behaviours Framework. e) Research managers should attend the relevant ‘Bangor Research Manager’ update workshop. f) Managers will be sent copies of the updated Guide to the Management and Employment of Contract Research Staff. | I. See success measures EC15 II. 50% of research managers have attended sessions regarding the PBF III. 60% of research managers have attended the Research Manager Update | May 2022 | Research Managers |  |  | New
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | a) All research managers to be sent information regarding the new Health and Wellbeing Strategy to ensure that they are aware of how they should support staff. b) All research managers will be sent an updated version of the Dignity at Work and Study Policy which should be shared with staff. | I. See success measures ECI3 II. 70% of staff note that their manager promotes a good work life balance (CEDARS) III 75% Staff feel included within my immediate research environment / research group (CEDARS) | a) July 2021 b) Jan 2021 | Research Managers |  |  | P6.9
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | Presentations regarding Employee Support will be provided in each College to ensure that staff are aware of institutional policies and flexible working. | Presentations given in Colleges on an annual basis and managers have encouraged staff to attend. | May 2022 | Research Managers |  |  | New
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Ensure managers respond to consultation through the surveys and encourage staff to engage with University, College and School consultation. | I. Over 50% response rate by researchers to CEDARS and Staff Survey. II. Relevant positions in committees occupied by research active staff and encouraged by manager to participate in relevant events in PDRs and informally | May 2022 | Research Managers |  |  | New
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | a) Ensure all researchers have completed the mandatory on-line equality training. b) Ensure new staff attend the Researcher Induction or engage with the on-line induction presentations. c) Engage with University / College / School research events and ECR Network. d) Research staff should support the school induction process to ensure that new staff feel supported. e) All staff to be sent a Guide to Equality in Bangor to ensure that they are aware of their responsibilities in relation to supporting an inclusive research environment. | I. See success measures EC13 and EC14 II. 20% increase in research staff attending ECR Network and researcher development events. | a) May 2022 b) March 2021 c) May 2022 d) March 2021 e) March 2021 | All researchers |  |  | New
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | a) Ensure researchers are aware of their contribution to researcher integrity policies through familiarity with relevant policies and attendance of relevant sessions on research ethics / integrity. b) Engage with sessions / on-line guides in relation to the Professional Behaviours Framework. | I. See success measures EC15 II. Ensure 90% of all researchers have completed the mandatory on-line equality training III. Ensure new staff attend the Researcher Induction or engage with the on-line induction presentations IV. Monitor participation levels and aim for 50% researcher participation rates in University events | a) May 2022 b) March 2021 c) May 2022 d) Dec 2021 | All researchers |  |  | P5.3
ECR3 | Take positive action towards maintaining their wellbeing and mental health | a) Researchers will be sent information regarding the range of support provided to them in this area. b) Information is sent to researchers to ensure that they are aware of the University and local development events that are provided. | I. See success measures ECI4 II. 70% of researchers take positive action to maintain my wellbeing and mental health (CEDARS) III. 80% of researchers have good mental health and emotional health and wellbeing (77% Staff Survey, 2020) IV. 70% of researchers feel they have good physical health and wellbeing (65% Staff Survey, 2020) | Ongoing | All researchers |  |  | New
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | All Research staff to be sent an updated version of the Dignity at Work and Study Policy to ensure that they are aware of how to report incidents of bullying and harassment | See success measures ECI3. | Dec 2020 | All researchers |  |  | P6.9
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | a) Researchers should respond to relevant surveys to ensure that a broad range of views are expressed in the surveys. b) Consider joining, and engaging with relevant committees. | I. Over 50% response rate by researchers to CEDARS and Staff Survey II. Relevant positions in committees occupied by research active staff | a) May 2022 b) Ongoing | All researchers |  |  | P3.13
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | a) Review recruitment and selection training for researchers to ensure that staff are confident in managing the recruitment and interview process. b) Review best practice in relation to on-line interviews and develop a best practice guide for staff. | 90% of research staff believe that their recruitment, selection and appointment was fair (CEDARS) | a) Dec 2021 b) Dec 2021 | a) DDHR(O) b) DDHR(O) |  |  | P1.2 P6.2 P6.7
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | a) Increase the number of on-line induction presentations particularly for part-time researchers. b) Undertake a review of local induction in the Schools to standardise induction and share best practice across the Schools. c) Discuss with HR Operations the possibility of including information regarding researcher induction in staff contracts. | I. 50% of researchers find the University Welcome induction useful (38% CROS, 2019) II. 70% of researchers find the Researcher Induction useful III. 70% of researchers find the School induction useful (46% CROS, 2019) | a) Dec 2020 b) July 2021 c) Dec 2020 | a) HRO(SD) b) HRO(SD) c) AS&RCM |  |  | P3.6
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | a)Following the review of academic promotion criteria hold sessions to communicate the new; policy, guidance and criteria to research staff to ensure that they can develop their academic profiles effectively and plan their career development. b)Evaluate the effectiveness of these sessions. c)Ensure that staff are aware of the importance of good citizenship through undertaking administrative and leadership roles in the academic promotion process. d)Review the research staff opinion regarding the new process following the first round of the new process. | I. 70% of researchers believe that promotion pathways and processes at Bangor are clear (CEDARS) II. 80% of researchers believe that Bangor has fair and inclusive opportunities based on merit for career progression and promotion (CEDARS) III. Grant/funding applications – 60% of research staff agree (50% CROS, 2019) IV. Publication and other research outputs – 75% of research staff (68% CROS 2019) V. Supervising or managing staff – 50% (27% CROS, 2019) VI. Supervising research students – 60% of research staff (40% CROS, 2019) VII. 70% of researchers believe that promotion pathways and processes are clear (CEDARS) VIII. 80% of researchers believe that Bangor has fair and inclusive opportunities based on merit for career progression and promotion (CEDARS). | a) Sept 2021 b) Sept 2021 c) Sept 2021 d) Sept 2021 | a) DDHR(D) b) DDHR(D) c) DDHR(D) d) DDHR(D) |  |  | P2.6 P6.3 P6.4 P6.7
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | a)Continue to run and evaluate the Research Leadership Programme. Adapt and develop in response to the feedback. b) Annually run a series of leadership talks for Research Leadership Alumni. c) Work with the participants of the Research Leadership Programme to develop a programme based on the practical elements of managing research projects with the intention of developing a programme to be run annually. This would also be provided on Blackboard. d) Make researchers aware of the ‘Women in Leadership’ action plan and encourage their engagement with the planned events and activities i.e. women in leadership mentoring. | I. One programme run per academic year with 80% of attendees noting that their overall opinion of the Programme was excellent. II. Annually run 2 leadership talks for Research Leadership Alumni with over 60% finding them useful. III. Programme available on Blackboard. | a) Sept 20 and ongoing b) January 20 and ongoing c) July 2021 d) July 2021 | a) DDHR(D) b) DDHR(D) c) SDT/RIIO d) DDHR(D) & AS&RCM |  |  | P2.3
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | a)To ensure all research staff are aware of their responsibilities in relation to the Concordat prepare a statement for Deans / Heads of Schools PIs/Research Managers and a statement for research staff outlining the expectations of the University in relation to the Concordat e.g. the requirement to engage in annual PDRs, professional development etc. This commitment will be reviewed annually in PDRs. b)Ensure all PIs/Research Managers receive training regarding the new ePDR process. c)Ensure developments regarding the new WAM model are communicated to research staff. d)Introduce an award for good PI citizenship to recognise effective research leadership. Profile the winning applications on updated Staff Development Leadership pages. | I. 80% of research staff have participated in PDR in the last two years (73% prof/reader, 61% T&R lecturer, 66% RO staff, Staff Survey 2020) II. 80% of research staff have found it very useful/useful (68% prof/reader, 73% T&R lecturer 66% RO staff, Staff Survey, 2020) III. 60% of research staff agree that their manager promotes a good work life balance (CEDARS) IV. 50% of research staff note that they are not struggling to cope with the volume of their current workloads (31% Prof/Readers, 34% T&R Lecturing staff, Staff Survey 2020) V. See success measures ECI1 | a) Dec 2020 b) July 2021 c) July 2021 d) May 2022 | a) AS&RCM b) DDHR(D) c) PO(WAM) d) DirHR |  |  | P2.6 P6.3 P6.4
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | a) Take a base line this year of research staff who have fixed term contracts and identify those who have worked for the University for more than four years and are eligible to be transferred to open contracts. b) HR Operations Team to set up an annual process by which research staff on fixed term contracts are reviewed and transferred to open contracts if they are eligible. c) Update the current fixed term contract policy. d) Improve the end of contract process for fixed term contract staff to ensure that decisions can be communicated sooner and support provided to staff if necessary. e) Ensure that staff on fixed term contract have parity of access to induction, training and mentoring | I. For those eligible to be transferred to an open-ended contract (over 4 years service and no justifiable objective to remain fixed term), 100% to be converted to open ended contracts. II. 80% of staff on fixed term contracts feel valued by the University (60% all staff, 70% fixed term staff - Staff Survey) III. 80% of fixed term staff feel valued by the University (60% all staff, 70% fixed term staff - Staff Survey) IV. 85% of fixed term staff feel that they are given the same opportunities to develop as other staff (68% all staff, 79% fixed term staff, Staff Survey). | a) Dec 2020 b) Sept 2020 c) Sept 2020 d) Dec 2020 e) May 2022 | a) DDHR(O) b) DDHR(O) c) DDHR(O) d) DDHR(O) e) DDHR(D) |  |  | P1.3 P2.1 P2.2
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | See ECI6 | See success measures ECI6 | Ongoing |  |  |  | P3.13
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | [6 empty] | P2.4
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | [6 empty] | New
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | [6 empty] | P2.4
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | [6 empty] | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | a) Managers must engage with the Manager Updates for staff to ensure that they are aware of relevant policies. b) Research managers should be aware of the resources available to them e.g. The Guide to the Management and Employment of Contract Research Staff. c) Ensure in PDRs that managers of researchers are attending relevant workshops and ensure effective induction for new staff | In the CEDARS survey managers note that: I. 90% are confident in my ability to be inclusive, equitable and transparent in recruitment practices (88% PIRLS, 2019) II. 90% actively support my researchers in working towards their promotion aspirations III. 80% to manage the appraisal process effectively (52% PIRLS,2019) IV. 80% to provide effective feedback to individual researchers V. 80% respond to any issues relating to health and wellbeing | a) May 2022 b) May 2022 c) July 2020 | All research managers |  |  | P2.3
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | Managers should be aware of the available support and policies relevant at the contract and post-award stage. | See success measures ECI3. | July 2022 | All research managers |  |  | P2.2
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | a) Managers must ensure that they have attended the relevant recruitment and selection workshop to ensure a fair recruitment process for researchers b) Managers should be familiar with the promotion criteria in order to advise researchers regarding career progression and promotion in their team. | See success measures ECI5. | Ongoing | All research managers |  |  | P6.3
EM4 | Actively engage in regular constructive performance management with their researchers | a) Ensure with the introduction of the ePDR system that all PIs / research mangers attend relevant training to ensure that they hold effective PDRs for staff. b) Heads of Schools/ PIs/Research Managers will discuss the statement of expectations with their reviewees to ensure that the expectations are cascaded to all resaerch staff and enusre that are engaging with the principles of the Concordat. c) PIs / research mangers should be aware of the development opportunities and resources available for staff to develop their skills and knowledge. d) Mangers should be aware of the Performance Management Toolkit | I. 100% of research managers have attended ePDR updates II. 100% of research managers have attended ePDR updates III. 100% of research managers have attended ePDR updates IV. See success measures EI5 V. See success measures ECI1 |  | All research managers |  |  | P2.3
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | See aims in ECM5. Also, managers should encourage their teams to engage in consultation initiatives and policy development. | See success measures ECM5. | Ongoing | All research managers |  |  | New
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | All researchers should be familiar with the relevant policies and the behaviours expected by researchers in the University. | See success measures EI2. | Ongoing | All researchers |  |  | New
ER2 | Understand their reporting obligations and responsibilities | See EM2 | See success measures EI2. | Ongoing | All researchers |  |  | New
ER3 | Positively engage with performance management discussions and reviews with their managers | All researchers should proactively engage with the PDR process to ensure that they are clear about their objectives, are aware of career development opportunities available to them and the Concordat statement of expectations for research staff. | See success measures EI5 | Ongoing | All researchers |  |  | P5.6
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | All researcher should engage with the Staff Survey and CEDARS survey. | See success measures ECR5 | 2022-05-01 | All researchers |  |  | P5.2
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | a) Evaluate the Academic Mentoring Scheme and act on any recommendations that arise. b) Review mentoring at School level to ensure that local mentoring is effective. c) Ensure that research staff are aware of the development and mentoring opportunities available to them. d) Develop through consultation with relevant research groups and Colleges a University Policy and Guidance regarding the implementation and the broad range of activity that can be included within 10 days professional development. e) Integrate a monitoring process for CRS and ECRs within the PDR sysem to ensure they have accessed at least 10 days professional development. f) Examine how to maximise development opportunities provided for ECRs and the Doctoral School. g) Improve reporting of training uptake to Colleges and Schools with the intention of sending three reports per annum reporting on uptake on the range of; development courses available to staff, central mentoring schemes, equality training and leadership training. | I. 90% satisfaction with the Academic Mentoring Scheme in annual evaluation II. 70% satisfaction in annual evaluation of the local evaluation III. 60% of participants agree that the initiative is useful / very useful. Also, in CEDARS In 4 years 80% of ECRs note that they have received 10 or more days spent of training and CPD pro rata, per annum. | a) Sept 2020 b) Dec2020 c) Dec 2020 d) Sept 2021 e) Dec 2021 f) July 2021 g) Ongoing from Dec 2020 | a) HRO(SD) b) HRO(SD) & HoS c) AS&RCM & RIIO d) PVCRII e) DD(HR)D f) Ch – RDCG & DPGR g) HRAdmin |  |  | P3.1 P3.3 P5.5
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | a) Annually report on PDR completions for researchers. b) Review the quality of reviews following the introduction of the ePDR system in Schools. | I. See success measures EI5. II. Completed and results fed into on-going PRD development for reviewers III. 70% note that your manager encourages you to engage in personal and career development activities (CEDARS) | a) Oct 2020 & annually b) Dec 2021 | a) HRTG &SCG b) HRTG & SCG |  |  | P3.10
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | a) Evaluate the Career Development Programme and implement recommendations for the next Programme. b) Examine how to expand career support to researchers. c) Identify Bangor University Alumni who can provide advice regarding different career pathways. | I. 60% of participants note that the Programme is useful / very useful II. CEDARS survey results - that 60% of staff agree that their manager encourages them to consider a wide range of future career options within and beyond academia | a) May 2021 b) Dec 2021 c) Ongoing | a) RDCG&SCG b) RDCG&SCG c) AS&RCM |  |  | P3.1
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | a) Communicate fellowships that are available for staff and encourage staff to apply for fellowships e.g. UKRI and run a series of workshops to support staff making applications for fellowship and engage with external bodies such as the Learned Society of Wales. b) Award a minimum of two of the research and impact projects from the University’s HEFCW GCRF Fund to Principal Investigators (PIs) who are ECRs. ECR eligibility is based on whether the applicant has had a permanent academic post for less than 5 years. c) Continue to encourage staff to engage with the Welsh Crucible. d) Continue to encourage staff to engage with the Research Leadership Programme. e) Review current profile of staff with fellowships. a Society of Wales. | I. Complete review current profile of staff with fellowships. II. 60% note that you have time to develop your research identity III. 60% note that you have time to develop your leadership skills | a) May 2022 b) July 2021 c) Ongoing d) Ongoing e) July 2021 | a) DirRIIO b) DirRIIO c) DSM d) DDHR(D) e) AS&RCM |  |  | P3.11 P3.14
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | a) Following the first Career Development Programme for researchers examine how best to share information regarding careers outside HE to researchers. b) In exit surveys collect information regarding next role for researchers to understand career stages of researchers. This will help inform future support for researchers. | Completed and reviewed. | a) Dec 2021 b) July 2021 | a) RDCG & SCG b) DDHR(O) |  |  | P3.2 P3.4
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | a) Produce annual training and development report to be distributed to all Colleges / Schools | Completed and reviewed. | a) Oct 2020 & annually | a) HRAdmin |  |  | New
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | [6 empty] | P3.7 P3.9
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | [6 empty] | New
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | [6 empty] | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | a) All mangers should hold a PDR with researchers and discuss their short and long term career development as part of this process. | See success measures EI5 | Ongoing | All research managers |  |  | P2.3
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | a) Ensure that managers are aware of the opportunities available in the University and externally and encourage staff to participate in the Careers Development Programme. | CEDARS survey: I. 70% of staff agree that their manager engages them in personal and career development activities II. 60% of staff agree that their manager encourages them to consider a wide range of future career options within and beyond academia | Ongoing | All research managers |  |  | P3.4 P3.8 P5.5
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | a) Identify a wide range of development that researchers can engage with to ensure that researchers undertake a minimum of 10 days development b) Managers to ensure that that part-time researchers can also access training. | See success measures PCDM2 | Ongoing | All research managers |  |  | New
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | a) Identify a wide range of development opportunities that researchers can engage with to ensure that researchers undertake a minimum of 10 days development b) Managers to ensure that that part-time researchers can also access training. | See success measures ECDI5 | Ongoing | All research managers |  |  | P3.6 P3.9 P5.5
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | All research managers should engage with leadership training in order to improve their skills as research leaders and be a role model for their teams. | See success measures EM1 | Ongoing | All research managers |  |  | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Use and engage with the PDR process to reflect on their progress towards their career goals and identify development opportunities to support their career development. | See success measures PCDI1 | Ongoing | All researchers |  |  | P5.5
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | a) All researchers should engage with the University’s mentoring programme when appropriate and explore options to develop their skills and knowledge. b) Engage with the Career Development Programme and associated resources. | See success measures PCDM2 | Ongoing | All researchers |  |  | P3.8
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | a) Keep their professional development plan up to date through the annual PDR. b) Keep their PURE profile up to date | I. 70% of research staff agree that they have a career development plan (53%, CROS, 2019) II. 100% of staff keep their PURE profiles up to date | Ongoing | All researchers |  |  | P5.5
PCDR4 | Positively engage in career development reviews with their managers |  | See success measures EI5 | Ongoing | All researchers |  |  | P3.10
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | All researchers should engage with the wide range of development opportunities available to them | 80% of research staff note that they have time to develop their broader leadership skills (CEDARS) | Ongoing | All researchers |  |  | P5.5
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | All researchers should engage with relevant opportunities and engage with RIIO and their Colleges to develop their knowledge and contributions in these areas. | See success measures PCDI5 | Ongoing | All researchers |  |  | P5.2
GLOSSARY
AS&RCM - Athena SWAN and Research Concordat Manager
CEDARS - Culture, Employment and Development in Academic Research Survey
Ch-RDCG - Chair Researcher Development & Concordat Group
CEG - College Equality Groups
CROS - Careers in Research On line survey
DDHR(D) - Deputy Director HR (Development)
DDHR(O) - Deputy Director HR (Operations)
DirHR - Director of HR
DPGR - Dean of Postgaduate Research
DS - Doctoral School
DSM - Doctoral School Manager
HRAdmin - HR Administrator
HRO(SD) - HR Officer (Staff Development)
HRTG - HR Task Group
PDR - Performance Development Review
PIRLS - Principle Investigators and Research Leaders Survey
PO(WAM) - Project Officer WAM
PURE - PURE Research Information Management System
PVCRII - PVC Research, Innovation and Impact
RDCG - Researcher Development & Concordat Group
RDCGRep - Researcher Development & Concordat Group College Representative
RDF - Researcher Development Framework
RIIO - Research Innovation and Impact Office
SCG - Strategic Concordat Group
SHRO(Eq) - Senior HR Officer (Equality)
UASWG - University Athena SWAN Working Group
H&WG - Health & Wellbeing Group
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.